## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Group #5
| Project | Pizza Ordering System
| Product Owner | Euphrates Youngblood
| Scrum Master | Nailah Williams
| Development Team | Justin Spratt, Kyle Simmons, Derek Valenzuela, Kylie Uffens, Cheng Vang
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
S7 | User Friendly Site | As a customer, I don't want to be confused when I visit this site so I can navigate it easily. | Clear navigation, Contrasting Colors, Simple Menus | 1 | 1 | Kyle
S12 | Browse Menu & View Photos | As a customer, I want to view the full menu with desciptions, photos and pricing so I can decide what to order | All active menu items desciptions, photos, and prices are visible. Discounts and Promotions are visible. | 1 | 1 | Kylie
S8 | Simple Updating | I want the store manager to be able to update menu items, photos, and prices whenever needed. | Self Explanitory Menus, Quick Update Times | 2 | 1 | Derek
S1 | Place an order | As a customer, I want to submit my order after checkout so the restaurant can prepare it. | Order submission requires a valid cart, required customer info, and successful payment. Customer sees an order confirmation page. | 3 | 1 | Justin
S3 | Customer Info | Customer information should only include what’s needed for orders (name, phone, address, order details). | Maintain minimum amount of info | 4 | 1 | Cheng
S5 | Handle payment failures gracefully | As a customer, I want clear error messaging if payment fails so I can retry or choose another option without losing my order. | Failure shows an actionable message (retry, change method). Cart/order details remain intact after failure. | 5 | 1 | Justin
S6 | Secure Payment Options | As a customer, I want to feel confident that my payment information is not liable to attacks so I can feel safe shopping on this site. | Authentication & Authorization, Encrypted Sensitive Data, Fraud Detection and Protection | 1 | 2 | Derek
S9 | Auto Payment Calculating | Make sure the website automatically calculates the final bill based on their selections. | Final bill amount calculated fully automated after location information provided | 2 | 2 | Kylie
S4 | Order confirmation details | As a customer, I want to see an order summary (items, total, contact/address) so I can verify what I submitted. | Confirmation displays items, totals, and customer-provided details. Confirmation provides a basic reference number. | 3 | 2 | Justin
S10 | Essential Store Info | I only want essential restaurant information displayed: menu, photos, hours, discounts, and promotions. | Maintain minimum amount of info | 4 | 2 | Derek
S2 | User Account | I do not need customer accounts, logins, or saved profiles for this version. | Details needed for order should be gathered during point of sale. | 5 | 2 | Kyle
S11 | Scalable Order System | I want to be confident that my order system will not overload as my business grows | System can process at a defined baseline, Elastic Resource Management | 5 | 2 | Cheng

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Pizza Ordering System
|  | Sprint # |  | 1
|  | Start date |  | 2026-05-05
|  |  | Total Team Members | 7
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18
SP1-TO1 | S7 | Create a clear Site Structure (Sitemap, Global Nav, Labels, Local Nav if Needed) | Kyle | 2 | 2026-05-11: 4; 2026-05-12: 4
SP1-TO2 | S7 | Establish Consistent UI Rules (Typography Scale, Spacing Rules, Color Choices with Contrast in Mind) | Derek | 1 | 2026-05-11: 3
SP1-TO3 | S7 | Easier to use, Harder to mess up (Keybaord Nav, Labels for form inputs, Focus states visible) | Kylie | 2
SP1-TO4 | S3 | Design Customer Data Model (Name, Email, Phone, Address, ID) | Justin | 1 | 2026-05-12: 3
SP1-TO5 | S3 | Require Login for Access | Cheng | 1 | bar: 2026-05-13; 2026-05-16
SP1-TO6 | S3 | Encrypt Sensitive Data (If Applicable) | Justin | 2 | 2026-05-12: 4
SP1-TO7 | S1 | Validate Cart and Customer Info | Derek | 2 | 2026-05-11: 3
SP1-TO8 | S1 | Generate Order Confirmation Page | Cheng | 1 | 2026-05-14: 2
|  | Remaining units (actual) |  | 112 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 102 | 91 | 90 | 88 | #N/A | 87 | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
[10 empty] | 0 | 12 | [5 empty] | 0 | 10
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Pizza Ordering System
|  | Sprint # |  | 2
|  | Start date |  | 2026-05-19
|  |  | Total Team Members | 7
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01
SP2-T01 | S6 | Define payment processing approach (hosted checkout vs. payment intent) and document “no card data stored” rule | Cheng | 2 | 2026-05-31: 2
SP2-T02 | S6 | Create payment data-flow diagram (client -> provider -> server) and identify trust boundaries | Derek | 2 | bar: 2026-05-31
SP2-T03 | S6 | Enforce HTTPS-only in deployment plan (and HTTP to HTTPS redirect if applicable) | Justin | 1 | bar: 2026-05-19 to 2026-05-20
SP2-T04 | S6 | Implement payment initiation endpoint (server creates payment session/intent) | Justin | 3 | 2026-05-19: 1; 2026-05-20: 1; 2026-05-21: 2; 2026-05-30: 1
SP2-T05 | S4 | Check with client to see how they want order confirmation displayed (simple text layout, additional text describing wait time , etc) | Kylie | 1 | bar: 2026-05-27
SP2-T06 | S4 | Establish data pipeline from "place order" system to "order confirmation" system | Justin | 2 | 2026-05-20: 2
SP2-T07 | S9 | Take items from cart and calculate subtotal | Kyle | 1 | bar: 2026-05-25 to 2026-05-26
SP2-T08 | S9 | Establish local tax costs and calculate final total | Kyle | 1 | bar: 2026-05-26
|  | Remaining units (actual) |  | 112 | 110 | 106 | 104 | #N/A | #N/A | #N/A | 103 | 101 | 100 | #N/A | #N/A | 99 | 96 | #N/A
|  | Remaining units (ideal) |  |  | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
[10 empty] | 0 | 13 | [5 empty] | 0 | 1
[10 empty] | 10 | 0 | [5 empty] | 10 | 0